AUSTRALIAN BROADCASTING CORPORATION

DISABILITY ACTION PLAN REPORT

DECEMBER 1998

Employment

Target:  By 2000, the representation of people with disabilities employed by the ABC to be at least 5% of total staff.

Aim:  To ensure that people with disabilities have access and equity in all areas of employment.

Recruitment and Selection

Goals

Encourage internal and external people with disabilities to apply for positions and opportunities within the ABC.

Ensure that people with disabilities are not disadvantaged by the recruitment and selection processes.

Strategies	Responsibility	Performance Indicator	Time

1. Develop guidelines for the assessment of PWD including:	Human Resources (HR)	Guidelines developed and distributed.	September 1997

*  identifying inherent requirements of the job;

*  suitable methods of assessment; and

*  extent to which reasonable adjustment should apply.

Progress: Discussions held with HR Policy Personnel, resolving that the emphasis for guidelines should be on individuality, abilities, needs and merit.

Further Recommendation:  Basic principles to be written and incorporated in revised Employee Selection Guidelines, aided by Management Training in Reasonable Adjustment.  These will be written by the new National Recruitment Manager.

2. Review existing guidelines for staff on selection procedures to 	HR	Guidelines reviewed and updated where necessary.	June 1997

cover PWD.

Progress:  The ABC's Employee Selection Guidelines are currently being re-drafted as negotiations between Unions and Management continue.  However, the needs of PWD have been discussed with those involved in those negotiations.

Further Recommendations:

- Ensure needs and practicalities addressed when Guidelines re-drafted.

- Ensure that Guidelines include that when there are tests or examinations to be undertaken by candidates for a position or by potential Trainees, appropriate adjustment be made where necessary to improve equity of access and fairness for PWD.

- 3. Examine PWD recruitment issues including:	HR	Contacts and list of organisations and publications	June 1997

- *  liaison with PWD organisations;		established and maintained.

- *  where to advertise; and

- *  support mechanisms required

- Progress:  Most specialised publications specifically for PWD do not appear frequently enough to make it viable to advertise ABC jobs, but lists of publications have been updated extensively and may be used to carry any other information about ABC initiatives under the DAP.

- Since the disbanding of the Commonwealth Employment Service, recruitment of PWD is scattered.  Up to date list of organisations currently engaged in this work already compiled and disseminated to Portfolio Heads.  Will need updating periodically as all are now competing for clients and new ones emerge as old ones disappear.

- Further Recommendation:

- Ensure definite procedures are developed in order that all external positions are advertised as widely as possible,  through the new National Recruitment Manager.

- 4. All advertisements for positions to include a reference to	HR	References included in advertisements.	Ongoing

- the availability of TTY service and of information about

- vacant positions in alternate formats for people with a print

- disability.

- 5. Provide position description documentation in alternate formats 	Corporate HR	System set up for Disk/tape formats.	Ongoing

- such as disk or tape.

- Progress:  Established that although the ABC already possesses a TTY (Telephone-Typewriter) line, this is allocated exclusively for the receiving of feedback on and enquires about TV Programmes.

- Investigated the practicalities of Position Descriptions being available in alternate formats on request.  Concluded that most ABC offices have a photocopier complete with enlarging facility, a computer system capable of loading a "Text" file on to disk, reading a Position Description on to tape.  Braille facilities are also accessible through at least one ABC staff member for short documents such as job applications.  The local Blind Society may be able to help but is often unable to complete jobs on short notice.  Preparedness to dispatch Position Description via Fax or Email would also further enhance potential for equal access.  Guidelines dealing with the practicalities of some of the alternate formats prepared for National Recruitment Manager for distribution where required.

- Further Recommendations:

- Establish a second national 1800 TTY line in Human Resources, potentially in the office of the National Recruitment Manager, specifically for recruitment, employment and traineeship enquiries.

- Ensure each job advertisement carry Fax and TTY numbers as well as a phone number for enquiries.

- Ensure that when jobs are advertised with a Web-Site address for further enquiries, and particularly before this practice becomes a standard component of job advertising, the web-site be made accessible to all, including PWD.

- Ensure all job advertisements carry a standard line to the effect that selection criteria and other relevant information available in alternate formats on request.

- These initiatives to be included in the revised Employee Selection Guidelines.

- 6. Develop and provide an information package for selection panel 	HR	Information package developed and provided	March 1998

- members for interviews that include people with known disabilities.		to panel as required.

- Progress:  Extensive discussions held with Human Resources Policy Personnel.

- Information to be covered sufficiently in revised Employee Selection Guidelines for selection panel members to be able to use as a guide.

- 7. Monitor the number of applications for promotions and acting	HR	Applications monitored.	Six month ongoing

- opportunities by PWD.			End June/December

- Progress:  Further discussions to be held regarding the tracking of promotions/opportunities when new HR database is implemented.

- 8. Examine and make recommendations regarding the 	HR	Recommendations completed.	March 1998

- possibility of employing people with disabilities under the

- Supported Wage System.

- 9. Examine and make recommendations regarding the	HR	Recommendations completed.	March 1998

- Intellectual Disability Access Program.

- Progress:  Commonwealth incentive schemes to encourage the employment of PWD are in a constant state of change.  Information on the latest of these, the Supported Wage System and the related Employers' Guide to Wage Subsidy, available from the ABC Equity and Diversity Unit and the office of the National Recruitment Manager.

- Although the Intellectual Disability Access Programme is still in existence on paper, it is not generally used.

- The 1994 supported Wage System and the linked 1998 Employers' Guide to Wage Subsidies have in effect taken its place.  These have a wider application, but are still designed specifically to assist people, whose disabilities make it extremely difficult for them to obtain work without additional help.

- The system is further complicated by the fact that administration of at least some of the Commonwealth incentive schemes has devolved to the States and it can take several enquiries to discover which recruitment organisation in each State holds the current contract.

- Further Recommendations:

- That the National Recruitment Manager keeps Human Resources Staff and Line Managers informed of the latest Commonwealth training and incentive schemes designed to encourage recruitment of PWD.

- Where there is an application form for a position or Traineeship, space be made available in the "Optional" section for an applicant to be able to refer to a disability if they choose to do so.

- Overall Recommendation:

- That these recommendations and other issues concerning the recruitment, selection and employment of PWD, with the emphasis on individuality and ability, be addressed and implemented as an integral part of the ABC's new Recruitment Policy when it is formulated in 1999.

- Training, Development and Support

- Goals

- Encourage people with disabilities to apply for training and development opportunities.

- Increase managers' awareness of their role in assisting the training and development of people with disabilities.

- Provide a supportive environment for people with disabilities.

- Strategies	Responsibility	Performance Indicator	Time

- 1. Managers to ensure that staff from EEO groups, including PWD,	All managers	Participation of PWD applying to	Ongoing

- to attend appropriate training courses.		attend training courses.

- 2. Managers to ensure that staff from EEO groups, including PWD,	All managers	Participation of  PWD applying to 	Ongoing

- to apply for promotions, acting and other internal opportunities.		and being appointed to internal opportunities.

- 3. Managers to ensure that staff from EEO groups, including PWD,	All managers	Participation of PWD staff applying and being 	Ongoing

- to apply for appropriate external development opportunities.		appointed to external development opportunities.

- Progress:  All Portfolio Heads have acknowledged and indicated support in regard to their responsibilities to ensure PWD have equal access to and receive encouragement in becoming involved with internal and external training courses, as well as acting and promotion opportunities.

- Further Recommendation:

- Incorporate these strategies in the handbook on managing PWD to be distributed to all managers.

- 4. Monitor the number of applicants for training courses by PWD.	HR	Applicants monitored.	Ongoing

- Progress:  Requested ABC Training provide regular statistics for monitoring the number of PWD applying for training courses.

- 5. Investigate external PWD support organisations and groups.	HR	Contacts and list of organisations and services	December  1997

- available, established and maintained.

- Progress:  The ABC's Equity and Diversity Unit maintains contact with a number of relevant organisations and this knowledge has been extended through the implementation of the DAP.  The system works both ways in that through this work many organisations are now also aware of the ABC's initiatives under the DAP.

- However, a full and formal list of support organisations is difficult to establish and maintain as services across the country are in many cases state based and scattered.  The easiest and most up-to-date access for most states is, or will be, through the new call centres and websites, a list of which will be found in the Program Makers Guide and be kept in the Equity and Diversity Unit.

- Further Recommendation:

- A formal list has been established by the Equity and Diversity Unit and updated on an annual basis.

- 6. Investigate external disability awareness training facilitators and	HR	Information on courses compiled. Courses

- sessions for staff and run courses if appropriate.		conducted and evaluated if appropriate.	December 1997

- Progress:  Supplied Training with names and contacts for and materials from outside organisations able to assist with disability awareness training for both Managers and Staff.

- Supplied ABC Training with packages to use as a basis for disability awareness training projects.

- Further Recommendations:

- Two  training videos with supporting training material be developed, and delivered nationally.  One targeting Program-Makers on the portrayal of PWD and the coverage of disability issues, and the other in the form of a "Hypothetical"  for all managers and staff on the theme, "Why employ PWD."

- Marketing potential for both of these packages, already acknowledged by ABC Marketing, be fully investigated.

- Broadcast potential of the "Hypothetical" be investigated for Television and Radio.

- Potential for the style guide from the Program Makers Guide be turned into posters for ABC newsrooms and program areas and/or installed on the ABC's bases system be investigated.

- Potential be investigated for information on accessible websites to be made available on ABC's own intranet sites.

- 7. Ensure training courses provide facilities for PWD (including	HR	Courses offered or promoted by the ABC	June 1998

- external courses promoted by the ABC) and that the availability		are accessible to PWD.

- of these facilities is advertised.

- Provide a range of suitable alternative training programs, if

- appropriate facilities for PWD not available.

- Progress:  Course facilities discussed with Human Resources, Training and Building Services staff.  Training have already reviewed physical access to their training facilities across the country, with variable results revealing in some cases need for possible future upgrading.

- Further Recommendations:

- Training to evaluate current content, delivery and location of courses and develop a list of possible alternate access for PWD.

- Copy of access review be given to property management as part of their national review of facilities.

- Training to include on their registration form an optional section that allows staff to nominate special needs such as course information available either in advance or in alternate formats.

- Outside organisations providing training to and for the ABC are made aware of the above recommendations when selecting venues and course content.

- 8. Include appropriate speakers at management and other training	HR	Training courses include appropriate speakers.	Ongoing

- courses to increase awareness of issues for PWD.

- Progress:  Some appropriate external speakers' information passed to Training.

- 9. Develop and implement appropriate modules on EEO issues, 	HR	Effectiveness of training evaluated.	June 1998

- including for PWD, in supervision/management, output courses

- etc.

- Progress:  All EEO sessions conducted in the past two years have included awareness raising of the DAP on the issues of PWD.

- 10. Consideration of inclusion of at least one PWD in any future 	Portfolio Heads	Traineeship position considered or 	When future

- traineeship schemes.		allocated for PWD.	traineeships

- offered

- Progress:  ABC News and Current Affairs advertised the annual intake of Cadets through Central Marketing Services, one of the major employment organisations specialising in the employment of PWD.  The potential recruitment as a technical trainee, of a specific applicant with a disability, was also investigated by News and Current Affairs.

- National Networks has agreed to target one traineeship in the next three years for a person with a disability and advertised their 1998 Traineeships through Central Marketing Services.

- ABC TV's Program Production has targeted one of the six 1998 Traineeships for a PWD.  This information was included in the advertisement and was published in the Press on Saturday, 21 November 1998.  The advertisement contained the information that Position Descriptions in alternate formats were available on request.

- The advertisement was also widely disseminated amongst specialised recruiting agencies and networks in an effort to reach as many potential applicants as possible.

- ABC Finance and Support Services recruits Trainees from among graduating students at the end of the academic year and has put forward a suggestion for regular targeting of two positions from this group.

- 11. Ensure staff are aware of behaviour that constitutes harassment/	All managers	Increased awareness of staff.	Ongoing

- discrimination and of appropriate methods of dealing with such

- issues.

- Progress:  All Portfolio Heads aware of behaviour that constitutes harassment or discrimination, and agreed to continue working towards increased awareness of both problems and solutions among staff.

- An updated brochure and posters on the ABC's Workplace Harassment Policy were distributed nationally, which includes information on disability discrimination/harassment.

- EEO sessions have included information about harassment and discrimination, including regarding PWD and the Disability Discrimination Act.

- 12. Provide work experience for PWD.	All managers	Work experience provided.	Ongoing

- Progress:  Most departments have reduced the provision of work experience, generally.  ABC News and Current Affairs has undertaken to let the two Universities with which they work know that Journalism students with disabilities are welcome to do their mandatory work experience with the ABC and all other Portfolios expressed a willingness for PWD to undertake work experience with them when requested.  A number of areas have provided work experience for individuals such as Darwin Branch.

- Provision of work experience will continue to be reported in the ABC's EEO Annual Report.

- 13. Determine for staff with known disabilities, appropriate workplace	All managers	Where appropriate, reasonable adjustment	Ongoing

- design including any additional requirements or aids to enable		made.

- maximum productivity by the staff member.

- Progress:  Portfolio Heads displayed practical positive attitudes towards the concept and realities of Workplace Adjustment.

- Further Recommendations:

- Material on legal obligations concerning Reasonable Adjustment to and in the workplace and general,  practical benefits of such practices be disseminated to all Managers and incorporated in Management training sessions.

- Kym Duggan, Lawyer from the Commonwealth Attorney General's Department, or suitable alternative, in consultation with the Disability Rights Unit at the Human Rights and Equal Opportunity Commission be approached to deliver training on the practical and legal aspects of Reasonable Adjustment, in forums to be determined.

- 14. Investigate the need and introduction of a network for PWD.	HR	Network formed if appropriate.	June 1998

- Progress:  Email prepared for transmission to all staff with the aim of investigating the interest in a network for staff with disabilities or staff with interests in the issues, and the relevance of discussions on current issues effecting them.  Staff will be asked if they wish to be included on emailing list of relevant information.  Information gathered on external networks.

- Further Recommendation:

- That such a network be established if warranted by staff interest.

- 15. In conjunction with the provisions of the ABC Enterprise 	HR/Portfolio Heads	Options researched and recommendations	December 1998

- Agreement 1996-98 consider options for flexible working		made.

- conditions, including home-based work options.

- Progress:  Discussions are continuing regarding overall Workplace Reform with the Unions and Senior Management.

- A six month pilot Teleworking project is underway, which is due to commence in early 1999.

- Further Recommendation:

- Monitoring and evaluation of the pilot Teleworking project will be undertaken and appropriate recommendations put forward.

- Redundancy and Redeployment

- Strategies							Responsibility		Performance Indicator				Time

- 1. Monitor and analyse statistics on redundancies and redeployment  	HR	Data monitored and analysed.	Ongoing

- to ensure PWD are not over / under represented.

- Progress:  Redundancy statistics collected for the EEO Annual Report.

- Communication

- Aim:  To ensure that the ABC's Disability Action Plan and outcomes are communicated widely.

- Goals

- •   Ensure that information about the ABC amenities, services and resources is widely available for people with disabilities in the Australian community.

- •   Ensure that information about the ABC's Disability Action Plan is communicated to all staff.

- Strategies	Responsibility	Performance Indicator	Time

- 1. Develop a Policy Statement on the employment and services for	HR	Policy Statement published.	March 1997

- PWD.

- Progress:  Policy Statement on employment of and services for PWD endorsed in April 1998 and widely distributed during the year and included in the 1997-98 EEO Annual Report.

- 2. Compile a list of publications targeted at PWD to publicise the	HR	List of publications compiled.	June 1997

- ABC's initiatives under the DAP.

- 3. Devise a method of ensuring that the Australian community is 	HR/Corporate	Method of co-ordination of publicising	September 1997

- aware of initiatives regarding the ABC's services for PWD.	Management/Portfolio	initiatives devised.

- Heads

- Progress:  The list of publications specifically targeting PWD substantially expanded and updated for the Employment section of the DAP is probably more applicable to informing the community of the ABC's initiatives in this area.  However, since many of the publications are little more than organisation news letters or technology companies' product updates, and since not all people with a particular disability will automatically receive or want to receive publications targeting them, further steps need to be investigated to spread the word.

- Included on the list are all contacts for RPH - Radio for the Print Handicapped - Stations, the staff and volunteers from which are keen to become involved with such publicity, seeing their services as complementary to rather than in competition with those of ABC Radio services.

- Work with RPH Australia has begun to extend these links, where mutually beneficial, perhaps through specific specialised programming, links through Web Sites and particularly through relevant promos and community announcements, both of which have been run throughout the latter half of 1998.  However, it should be noted that unlike the ABC, RPH Australia does not reach a wide audience or transmit to the entire country, cannot claim to aspire to high rating and does not attempt to have a general appeal to the wider Australian community.

- ABC's DAP Project Officer, Elaine Harris, took part in interviews and made promos for RPH Australia in August 1998, seeking feedback on public needs regarding equal access to ABC services, resulting in very practical and positive public comments which were collated and circulated to all relevant ABC departments by the end of 1998.

- A community announcement was placed in an edition of the Melbourne-based Braille and Talking-Book Library's monthly audio magazine, "Library Talk", seeking public feedback regarding equal access to ABC services.

- The DAP Project Officer also addressed the Executive meeting on December 9 1998 of the National Caucus of Disability Consumer Organisations to give a progress report on the ABC's DAP and seek further feedback.  The National Caucus comprises 10 peak disability organisations representing and working with PWD.

- Brief piece written on ABC DAP initiatives for the December edition of "Link" Magazine, a specialised national Publication produced by the Ability Network based in Adelaide.

- Further Recommendations:

- That ABC initiatives be publicised through ABC networks, thereby maximising access to as many people as possible.

- That public feedback on initiatives under the ABC's DAP and on the accessibility of ABC services be sought through ABC networks.

- The ABC continues to seek feedback on these initiatives from peak disability organisations and from interested individuals.

- That the public feedback continues to be monitored, compiled and disseminated to all relevant ABC departments, particularly as the strategies of the DAP are addressed and further recommendations implemented, in order to ensure that we are supplying services that meet the needs of PWD.

- 4. Prepare a brochure on the DAP for distribution to all staff,	HR	Brochure distributed.	June 1997

- including a section on better employment practices for disability

- issues.

- Progress:  Information gathered.  Release of brochure to coincide with training initiatives.

- 5. Prepare a booklet on managing staff with disabilities for	HR	Booklet distributed.	December 1997

- distribution to all managers.

- Progress:  Discussions with the Commonwealth Office of Disability reveal that many Departments and Organisations are moving away from information of this kind and stress that where such booklets are prepared the emphasis must be on integration, ability and individuality.  Information gathered.

- Further recommendation:

- Booklet to proceed and include information and strategies arising from the DAP.  To be ready when the training initiatives proceed.

- 6. Provide for the inclusion of information on the DAP in the	HR	Sessions conducted.	March 1997

- Workplace Harassment sessions.

- Progress:  All Workplace Harassment Sessions have included information on the DAP and disability discrimination/harassment.

- 7. Include information on DAP in induction kits/sessions.	HR	Information included in induction programs.	Ongoing

- Progress:  The DAP is mentioned in the ABC Induction Video currently being produced, and information has been provided on the DAP, to be included in the updated kit.

- Further Recommendation:

- That the brochure for all staff on the DAP be included in the Induction Kit.

- 8. All completed guidelines arising from strategies in the 	HR/Portfolio Heads	Guidelines distributed to relevant staff.	Ongoing

- DAP should be distributed widely to staff members.

- Progress:  Much information has already been distributed to Portfolio Heads, Policy Staff and Department Managers, the new 1998 Editorial Policies have been circulated to all staff, and many recommendations contained in this report deal with the distribution of specific material once developed to relevant personnel.

- 9. Provide, on a regular basis, information to EEO and Workplace 	HR	Information sent to Contact Officers.	Ongoing

- Harassment Contact Officers regarding legislative changes and

- other relevant issues regarding PWD.

- Progress:  EEO and Workplace Harassment Contact Officers are kept informed of legislative changes and other relevant issues regarding PWD, on a regular basis.

- 10. Encourage staff with disabilities to participate in fora for 	HR	Group discussions taken place including	Ongoing

- discussions on issues and practices relevant to them.		staff with disabilities.

- 11. Establish a network of staff with disabilities.	HR	Network of staff with disabilities established.	December 1997

- Progress:  Email prepared for transmission to all staff with the aim of investigating the interest in a network for staff with disabilities or staff with interests in the issues of disabilities, and the relevance of discussions on current issues effecting them.  Staff will be asked if they wish to be included on emailing list of relevant information.  Information gathered on external networks.

- Further Recommendation:

- That such a network be established if warranted by staff interest.

- 12. Include details of the DAP in the EEO Management Plan	HR	EEO Management Plan 1997-2000 completed.	December 1997

- 1997-2000.

- Progress:  During 1997/98 an extensive review of the management of EEO in the ABC was undertaken.  Recommendations included moving to an Equity and Diversity model, with the development of a new management plan to cover the period 1997-2002.

- This plan is currently being developed and the DAP is included as a module - linked to the plan's overall objectives.

- Building Services

- Aim:  To ensure that people with disabilities have access and reasonable adjustment in regard to ABC locations and facilities.

- Goal

- •   Ensure that ABC sites and buildings are accessible to staff and visitors with disabilities.

- Strategies	Responsibility	Performance Indicator	Time

- 1. Review access to buildings ensuring that PWD can freely enter	Finance and Building	Review and recommendations completed.	Ongoing

- and move around ABC sites.	Services (FBS)/HR

- Progress:  An initial review of all sites has been completed and it has been found that a number of sites are non-compliant in respect of access.  These sites include Tamworth, Perth, Gore Hill and Burnie.

- This initial review is being re-enforced by more comprehensive compliance audits that look at all aspects of disability access plus other property management issues (eg OH&S).  For information see schedule of sites where compliance audits have been completed or contact ABC Property Manager.

- Strategies are being developed for rectification work on those non-compliant sites, where practicable.

- 2. Develop policy and guidelines that meet the relevant standards to	FBS/HR	Policy and guidelines written.	December 1998

- ensure all ABC buildings are accessible to PWD.

- Effective consultation and participation with employees and

- external disability organisations to assist the development of

- effective guidelines.

- Progress:  Draft Accommodation Brief incorporating guidelines and standards has been prepared.  This is still to be finalised and  promulgated, however all new buildings are being assessed according to the guidelines.  For information see Accommodation Brief or contact ABC Property Manager.

- 3. Design a program to implement the policy and guidelines for	Portfolio Heads	Program and resources determined.	March 1999

- access to ABC sites and buildings for PWD.  Determine adequate	FBS/HR

- funds and other resources required to ensure compliance.

- Progress:  A program for implementation of the Disability access policy and guidelines has been incorporated into the on-going program of rationalising, relocating or refurbishing ABC accommodation.

- This is best  illustrated by the five year Strategic Plan for Regionals.  This Plan established priorities for the review of regional accommodation.

- Capital city accommodation arrangements are also subject to review with major projects in hand for Sydney, Brisbane, Perth, Canberra, Adelaide and Hobart.

- Recent examples of refurbishment in which Disability Access requirements were covered include Kalgoorlie, Rockhampton, Bega, Bunbury, Darwin and Collinswood.

- 4. Implement the Building Access Program for PWD so that all ABC 	Portfolio Heads/	All buildings meet standards and are accessible.	Ongoing

- buildings are accessible to staff and visitors with disabilities.	FBS/HR

- Progress:  As for three above.  Examples include:

- Bega - provision of lift.

- Ramps at Bunbury, Rockhampton and Wagga Wagga.

- Modification of Ultimo lifts.

- 5. Venues and conferences held by ABC staff must have appropriate	All staff	Inclusion with policy guidelines.	Ongoing

- access for PWD.

- Progress:  Included in accommodation brief which sets out guidelines and standards for ABC accommodation and venues - refer two above.

- 6. Review adequacy of  information currently sent to external 	FBS/HR	Information reviewed and necessary changes made.	June 1997

- interviewees regarding access to ABC buildings.

- Progress:  Preliminary discussions have focussed on an experiment to be trialed with an "Access Information" card in one of the capital cities, containing information about parking, stairs, lifts, availability of staff to assist, etc., that could be handed or sent out to visitors where appropriate, and the otherwise blank back of the card offered to ABC Marketing for space to carry a current, topical or timeless promotion.

- 7. Investigate after hours security systems to determine if there are	FBS	Investigation completed.	March 1998

- barriers for employees with disabilities.

- Progress:  Security systems in all ABC sites subject to review.  New corporate Security Policy developed and to be promulgated in early 1999.

- Corporate Policy requires site specific security systems to be put in place and this is currently occurring.  Examples include Collinswood and Canberra and action is proceeding for new access control security systems at Ultimo and Gore Hill.  It is expected that tenders will b called for Ultimo and Gore Hill in February/March 1999.

- Requirements for PWD being covered in site specific specification.

- 8. Access standards AS1428 must be met before any new building	FBS /HR	Standards met.	Completed

- is built, purchased or leased.  Such standards should be put into

- all tenders for new buildings, made where necessary and be

- mandatory for all modifications to buildings.

- Progress:  Access standards have been incorporated into specifications, tenders and contracts for all new or refurbished facilities.

- 9. Directional aids should be included in all ABC buildings to assist	FBS/HR	Display of appropriate signs.	Proceeding and on-going

- the visually impaired and blind people.			but target date of June 1998

- not met.

- Progress: The newly appointed National Manager, Property and Services is reviewing these requirements and where practicable aids have been incorporated into specifications for new and refurbished facilities.

- Existing facilities have not yet been provided with aids.

- 10. Reserved parking to be provided for staff and visitors with 	FBS	Designated areas created and instructions given.	Complete

- disabilities, and suitable instructions outlined to reception staff.

- Progress:  Specific parking has been provided at sites where possible and reception staff have been appropriately instructed.

- 11. Develop/update guidelines for the emergency evacuation of 	FBS	Guidelines developed/updated.	Ongoing

- building for PWD.

- Progress:  This action forms part of the general review of access as per Strategy 1 and compliance with AS1428 as per Strategy 8.

- There will be coverage of evacuation procedures in the ABC Procedures Manual.

- Programs, Services and Delivery

- Aim:  To ensure that ABC products and services are inclusive and accessible for people with disabilities.

- Goals

- •    Encourage program makers, journalists, broadcasters and presenters to provide information and opportunities for people with disabilities in programs and to portray

- this group appropriately.

- •    Maximise the provision of products and services for people with disabilities.

- •    Conform with the relevant sections on broadcasting included in the Commonwealth Disability Strategy - A Ten Year Framework for Commonwealth Depts and Agencies.

- Strategies	Responsibility	Performance Indicator	Time

- 1. Review the Editorial Policies determined by the ABC Board, to 	Portfolio Heads	Editorial Policies reviewed and recommendations	June 1997

- ensure that appropriate references are included regarding PWD.		made.

- Progress:  Revised ABC Editorial Policies and Code of Practice, were completed and distributed in April 1998 with appropriate references regarding PWD, and are to be quoted in the Guide for Program Makers being prepared under the DAP.

- The Editorial Policies have been Brailled for one member of staff and there has been a request for an abridged version, particularly those aspects pertaining to local programming, to be produced on tape for a staff member, with the master copy to be held in the ABC Library in Sydney.  A deliberate decision has been taken to produce the tape at an ABC studio using an ABC voice.

- Currently non-discriminatory language is used on all networks within the National Networks portfolio.

- 2. Consider the participation of  PWD on the ABC National Advisory	Corporate Management/	Participation considered and recommendations 	December 1997

- Council.	HR	made.

- Progress:  A wide range of PWD approached directly and invited to apply for membership of the ABC's National Advisory Council.

- A Community Service Announcement on the National Advisory Council also syndicated to all RPH stations through RPH Australia.

- One of the three vacancies on the Council was filled by a person with a disability.

- Further Recommendation:

- That representation on the ABC's National Advisory Council by PWD be encouraged as a regular and integral part of advertising to fill vacancies when they arise and that disability be taken into consideration along with such factors as age, gender, ethnic background, geographical location, etc., when applicants are short-listed and selected.

- 3. Examine information needs and appropriate formats to facilitate	Portfolio Heads/	Examination completed and strategies identified.	August 1998

- access for PWD including, where required, the translation of	Corporate Management

- public documents and other publications/brochures into Braille,

- audio tape or large print formats.

- Progress:  Feedback still being sought on the desirability and appeal of ABC Public Documents and Publications being made available in alternate formats.

- On disk in text format, through Web Sites, on tape, in Braille or Large Print are all options that have been raised as possible formats.

- Guidelines on the best and easiest way to approach each have been produced and distributed where appropriate, and are available from the ABC Equity and Diversity Unit.  By

- July 1999, a two-page hand-out on the most practical, cheap, effective and simple ways to approach the alternate formats be completed by Lynne Davis, on behalf of and with a grant from Blind Citizens' Australia (Sydney branch) and will be made available on request to all personnel through the ABC's Equity and Diversity Unit.

- Programs are currently available on audio cassettes through Radio Tape Sales and Triple J Morning Show interviews and stories are accessible by purchasing audio transcripts through library sales.

- Rick Nelson of the Disability Rights Office at the Human Rights and Equal Opportunity Commission has run a check on ABC Web Sites and prepared documentation demonstrating how existing access problems can be remedied at little or no cost.  These documents have been supplied to the ABC's Technology, Strategy and Development, Information Technology and Multimedia sections.  Mr Nelson has offered to visit and work with relevant policy personnel to assist in improving accessibility to ABC web sites and intranet sites.

- At present much of Triple J's information is accessible via the Internet.  The Multimedia Triple J website won the AFR/Telstra award for "Best Media Website".  One of the judging criteria was accessibility.  Triple J features many alt-tags and pays high regard to access issues.

- Recent selection process for in-house Graphics Designer strongly emphasised the application of graphics to web readability, useability and access.  Eg. by the inclusion of "alt-tags" which provide text-only information to people who can not easily read complex graphics or navigation tools.  The selection criteria also focused on EEO and web accessibility and the applicant's awareness of these issues.

- In February 1998 the Multimedia Creative Director and Senior Developer both attended a seminar run by the Law Foundation on disability access to the web.

- ABC Multimedia worked with RMIT in producing a CD-ROM which provides information on access to the internet for PWD.

- Discovered that "24 Hours" Magazine is already available on tape through the Royal Victorian Institute for the Blind (RVIB) in Melbourne.  However, at present they produce and circulate only 36 copies per month - the tapes are on loan, listened to and then returned for re-use - many people are unaware of the service.  National Networks also informs that "24 Hours" Magazine is available on audio cassette through Terraplane Press, though no price is specified. On-air promotion of this is to be followed up.

- ABC National Networks and Radio Marketing have been put in contact with Linley Wallace, Head of RVIB Library Services to establish a process to increase awareness.

- ABC Enterprises has been supplied with this information in order to assist when fielding enquiries.

- Since the Institute is funded by Government to provide services only to Victoria and Tasmania, it would be necessary to charge a subscription fee if the service were to expand to the rest of the country.  This potential expansion has been welcomed by the RVIB's Head of Library Services.

- Received a suggestion that RPH stations carry selected readings of articles from "24 Hours" magazine, and this idea has been circulated to all Managers of RPH stations across the country, with at least two already responding positively to the request.  Most stations already read out a daily program guide, although some limit themselves to Television, and would therefore be reluctant to repeat that component of the magazine.  However, the Magazine contains enough articles and other items to constitute a regular feature in its own right.  Thanks to the non-profit nature of these stations and the legislative framework within which they were established and are operating, this can be done without negotiating permission; copyright is waived automatically.

- Preliminary enquiries reveal that to make similar arrangements for the recording and distribution of the other regular publication associated with the ABC, "Gardening Australia", would be popular and well-received.  A proposal again welcomed by the Head of RVIB Library Services who has been put in touch with the executive producer of "Gardening Australia", in order to extend investigations.

- The ABC's DAP was transcribed to Braille in 1998 and two copies distributed.

- TTY Line

- During discussions with Portfolio Heads and policy makers, canvassed the possibility of spreading the word more effectively about the ABC's 1800 TTY Line, established exclusively for the receiving of feedback on and handling enquiries about ABC TV programs.  Switchboard and reception staff have been alerted to the existence of the number and arrangements made to have it included in the next edition of Telstra's TTY Directory and Ability Network's "Link" Magazine.

- Captioning

- On September 3 1998 the ABC delivered a submission to the Human Rights and Equal Opportunity Commission's review into Closed Captioning services in Australia.  Currently the ABC leads the country in the amount of Captioning offered but still the service is available to less than one-third of all programming.  The ABC included in its submission that due to the cost of providing Closed Captioning, though extending the service may be desirable it would be difficult without additional guaranteed quarantined funding.

- On December 10 1998 the ABC delivered its second submission to the review, this time in response to a Discussion Paper from the Human Rights and Equal Opportunity Commission.

- The Digital Conversion Legislation governing Digital Broadcasting, including Closed Captioning has been passed.  Government has called for submissions due 26 February 1999 on captioning standards.  The  ABC intends lodging a submission.

- Audio Enhancement

- Requests that any information displayed visually onscreen should also be available audibly have been passed on to relevant policy makers.  This applies particularly in the case of sports results, emergency or community information, programme details (such as time of screening) in promos, and in the use of subtitles where parts of programmes are spoken in a language other than English - the latter problem featuring predominantly, though not exclusively, in News-Bulletins, Current Affairs programs and Documentaries.

- Research already being undertaken by the ABC in conjunction with an outside company, Melbourne-based Information Alternatives, to ensure that onscreen only problems are avoided before the ABC makes the transition to digital technology.  However, much may still be done before that time and during the overlap period until the full establishment of digital technology.

- A team would be established to review policy options for audio enhancement.  The team would consist of key personnel from Presentation and Transmission and a number of Executive Producers.  The team will then determine policies that need to be put in place to ensure audio enhancement is included in programming where ever possible.

- Program Information

- During meetings with Portfolio Heads an idea evolved for the establishment of a hotline giving out daily details of ABC National Radio and Television programs.  This suggestion is proving extremely popular with Listeners and Viewers, judging from feedback received to date; some have gone so far as to suggest it be a Multiple Options number:  "Dial 1 for TV, 2 for Radio National, 3 for Triple J", etc.!

- Classic FM program information was available on a 0055 number, however, as this service had to be cost effective to be viable it was discontinued in 1998 due to low usage.

- Product Information

- Wider access for PWD to information about ABC products has been discussed with ABC Enterprises.  Already requests have been received for the ABC Catalogue to be made available in alternate formats.

- Copyright laws relating to the transcription of material into alternate formats changed in October 1998 and copies of the new guidelines have been distributed to ABC Enterprises and the ABC's Copyright Section.  In effect, it means that organisations specialising in production of material in alternate formats no longer need apply to publishers for copyright clearance; this could speed up transcription or recording of ABC publications by such organisations when requests for same are received by the ABC and forwarded on or dealt with internally.

- Further Recommendations:

- Links be forged between the ABC and the two key organisations for transcribing and recording material in alternate formats - the Royal Blind Society  of NSW in Sydney, and the Royal Victorian Institute for the Blind in Melbourne, in order to deal efficiently with requests for material as they come in.

- (The reason for selecting these two institutions from the very many in existence is that not only are they the largest established organisations involved in this work but also for audio material they are in the process of ratifying an agreement in an attempt to work together more closely and streamline services; more material will then be produced as less effort will be poured into unnecessary duplication.  When it comes to Braille editions of publications, there is already in existence the National Braille Service to which all such organisations subscribe with the result that if one service-provider transcribes an item, all other providers are notified automatically).

- ABC Web-sites and intranet services be fully investigated and access problems solved using the techniques available and the information supplied by the Human Rights and Equal Opportunity Commission.

- Guidelines on accessible web-sites, specifically tailored to ABC needs, be developed and issued to all staff responsible for their creation and maintenance, resulting in uniformity of access across all ABC web-sites.

- "24 Hours" magazine be made available on request in audio format through the Royal Victorian Institute for the Blind to the general community for $30 a year subscription fee, well below the annual purchase price of the print edition.

- RVIB's 1800 enquiries number be included both in the print edition of the magazine and as part of all "on air" promos.

- ABC Enterprises staff and all other personnel likely to field enquiries receive this information in order to supply it to customers where relevant.

- Appropriate systems be put in place to ensure the RVIB receive copies of the magazine with enough lead time to allow for its recording and distribution before the Program Guide contained within it becomes out of date.

- Enquiries be made about the relevance of a similar arrangement for the ABC's  other regular publication, "Gardening Australia".

- RPH Australia be offered the "24 Hours" and other relevant ABC Promos.

- As a matter of courtesy when playing recorded books to air, the Announcer state if and when the production is an abridged version.

- Information detailing whether or not a book is abridged be passed on to customers by ABC Enterprises staff as a matter of courtesy as well as a matter of course.

- The ABC becomes more pro-active in producing and/or organising copies of ABC books in alternate formats.

- Although ABC Audio reserves the right to make decisions about who should be engaged to read its audio books consideration be given to the idea that where the author is a well-known member of staff, particularly a Broadcaster with an instantly recognisable voice and style, he or she be the one to read the book on to tape for the audio production where suitable.

- The TV Feedback and Enquiries TTY number be promoted on ABC Television at appropriate times as a Community Service Announcement, and included in TV Guides in newspapers and other publications in the same place where Captioned programs are listed.

- The ABC TV program Web Sites, ideal to carry this information, and publications such as "Link" Magazine also publicise the number and service.

- Standard procedures are devised and put in place to ensure information given out onscreen is also automatically included in full measure in the audio component of a program or promo.

- The possibility of a national 1800 or individual locally-based Program Information Hotline be fully investigated and implemented if feasible, including a full publicity campaign and regular on air promotion.

- Once Web-Sites are fully accessible, Web-Site addresses for Program Guide information be promoted regularly on air.

- 4. Prepare an information guide for program makers that includes	Portfolio Heads/	Guide distributed.	December 1997

- contacts and suggestions for content on disability issues and	HR

- utilising people with disabilities as talent.  Specifically include

- information on the Arts and Disability Organisations in Australia.

- Progress:  A guide to be distributed to every program maker within the ABC is being prepared.  The guide will include contributions by high profile people, photographs of each contributor, two Cathy Wilcox Cartoons, information on the use and misuse of language - already discussed with SCOSE, Fact Sheets on Captioning, Audio Enhancement and Accessible Web Sites, and a comprehensive sources and resources guide containing recommendations for further reading, names and numbers of useful organisations, contacts and publications; these vary widely from state to state, and back up material for each state can be provided.  There will be a brief explanatory introduction and links between contributions and it is fully intended to be a practical working document as opposed to a forgotten publication gathering dust upon a shelf.  The guide will include a dedication to Elizabeth Hastings, former Disability Discrimination Commissioner with the Human Rights and Equal Opportunity Commission.

- The contributions received contain interesting challenges for program makers covering the whole gamut of ABC output and dealing sensibly with program content, portrayal, and attitudes.

- Further Recommendation:

- A video has been proposed which will include information and contributions from the program makers guide.

- 5. Investigate new technological developments and costs which	Head Technology	New developments investigated.	Ongoing

- may be of assistance to staff and audience/customers with	Strategy &

- disabilities.	Development

- Progress:  Work ongoing.  See references in this section to Captioning, Audio Enhancement, Web-sites and intranet services and Programme Information.

- 6. Continue to support Community initiatives for PWD such as	Portfolio Heads	Initiatives supported.	Ongoing

- the "Shine On" Awards, subject to editorial considerations.

- Progress:  Program content has been discussed extensively with Portfolio Heads and policy makers, as well as with members of the public who have taken the time to call in with responses.  Both "Link" Magazine and the Mood Disorders Association have undertaken to send multiple copies of their publications to the ABC complete with a one-page summary recommending stories for coverage and supplying contact details of reporters or appropriate key figures.  Both are providing this service exclusively to the ABC.  Doubtless as a result of these initiatives, other organisations and individuals may become more  pro-active, assisting the ABC in the promoting of positive attitudes as well as responding to coverage.

- Various networks have featured PWD and frequently cover disability issues.

- Many individuals and organisations consulted feel strongly about the portrayal of PWD in drama.  Researchers and Producers need to take the time to ensure the accuracy of representation, put far stronger emphasis on the individual than on the disability, and work towards "normalising" rather than the accentuating of negative differences.

- There were comments that disability issues are often marginalised; newsworthy issues treated as softer social comment stories, and social features presenting PWD either as "Super Achievers in spite of …", or pathetic objects of charity, instead of normal people with needs, aspirations and achievements not necessarily related to the disability.

- ABC Radio's Broadcast Rights Agreement with SOCOG for the Olympic Games, also applies to the Paralympics.  Some coverage will be provided on ABC Radio.  The position in Television is far more complex and much less certain, as there are two distinct areas to be considered - the role of Host Broadcaster and a domestic Rights Agreement.  ABC Television does not have the resources to fill the Host Broadcaster role unless funded separately to do so.  ABC Television would consider some measure of domestic coverage (whether 'live' or in the form of daily edited highlights) if a suitable Rights Agreement is joined.  However, this could also depend on the involvement of any Commercial network.

- The NSW State Department of Ageing and Disability commenced its Media Awards in December 1998 recognising and encouraging positive portrayal of PWD and coverage of disability issues.  Suggestions on how to avoid tokenism, make the awards fairer, and stimulate interest, recognition and acceptance from within the Media were requested and the ABC provided feedback from this office.  A list of NSW ABC Radio Stations and other useful and appropriate contacts was supplied to the Department of Aging and Disability, the ABC's State Manager for NSW is being kept fully informed and attended the official launch of the awards, and the ABC's George Negus chaired the ceremony launching the awards as well as writing a thought-provoking introduction to the media-kit dispatched around the state.  Since the awards are a long-term campaign rather than a one-off event, it is possible they may have a sustained impact on coverage, portrayal and program content.

- Worked with ABC Marketing, to develop proposals for the ABC to be represented at a major expo in Brisbane in March 1999, but on investigation the general purpose of the Expo rendered it inappropriate for the ABC to attend.

- Further Recommendation:

- Portfolio Heads encourage relevant staff to aim to produce program content that would be eligible for the Disability Media Awards.

7. ABC will continue to liaise with the Human Rights and Equal	Portfolio Heads/HR/	Liaison undertaken.	Ongoing

Opportunity Commission to ensure that we conform with the	Corporate Management

Broadcasts section of the Commonwealth Disability Strategy.

Progress:  Many aspects of the original Disability Strategy, including the Broadcasts section, are now out-of-date.  However, the Commonwealth Office of Disability is currently reviewing the Strategy after much lobbying for a shorter, pithier document, and their report should be released in early 1999.  The ABC's DAP is currently registered with HREOC and this report forms part of a progress report to HREOC.

Elaine Harris

Human Resources Project Officer

December 1998