ENET

Disability Action Plan

2007 to 2009

Our Organisation:

Essendon Network for Employment and Training Inc is a not for profit public benevolent Institution, incorporated under the Associations Act of Victoria 1981.

ENET employs 32 staff and is managed by a voluntary local Board of management.

ENET provides employment, education and training services, predominately to disadvantaged people living within the City of Moonee Valley and its surrounds.  ENET receives funding from Federal, State and Local Governments.

ENET offers a range of programmes and services that assist long, medium and short Term unemployed people, mature workers, people from culturally and linguistically diverse backgrounds, people with disabilities, young people, sole supporting parents and people who are socially disconnected due to substance abuse , domestic violence or other significant factors that impact on daily living.

Organisation aims and objectives:

Aim:

To be responsive to the employment, education and training aspirations of people with disabilties.

Objectives:

1. To assist these persons make the best use of employment, training or further education opportunities through the provision of appropriate services and resources.

2. To provide a facility that is accessible and appropriate to people with disabilities.

3. To encourage participation in ENET’s programmes and services by promoting an awareness in the community of ENET’s Disability Action Plan

4. In implementing a program to meet these objectives, the project will endeavour to make maximum use of resources available within the local and general communities.

Policy and Procedures:

Current Practices

Under the Australian Qualifications Training Framework ENET has in place an Access and Equity Policy for Enrolment in Training and Employment .

ENET recognises that particular groups of people in society have experienced and continue to experience, institutional disadvantage and unequal educational outcomes. Target groups include women, Aboriginal and Torres Strait Islanders, people of non-English speaking backgrounds and people with physical or intellectual disabilities.

This policy aims, therefore, to assist ENET to achieve best practice by promoting the establishment of strategies and processes that effectively redress past disadvantage and improve the position of all groups in society.

This policy also provides a framework for the development of policies and strategies that are aimed at achieving equal educational and vocational outcomes for target groups.

ENET treats every client fairly and without discrimination in its services and training environment. Grievance procedures have been put in place to ensure any concerns during training or employment placements, are dealt with immediately and appropriately.

ENET acknowledges its legal obligations under State and Federal equal opportunity law, including the Disability Discrimination Act, 1992 (Commonwealth)

Disability Action Plan:

Physical Barriers

Aims:

To improve physical accessibility to ENET’s premises and services

Outcome 1

People with disabilities are able enter and move within ENET’s Employment, Education and Training facility unhindered by physical barriers that might ordinarily restrict their participation in ENET’s services.

| Physical Barriers | Improvement Strategies | Timeframe | Performance Indicators | Resources Needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Entry to building Reception Information Desk Ensure appropriate space in training rooms for wheelchair access Access to toilets Corridors kept clear of obstructive items Stairs Install Lift Timetable downstairs training room Emergency fire exit Visual alarms | Install electronic door Provide access to reception that is lower than the existing height Design templates for each training room that demonstrates the best room layout for PWD needing wheelchair access Investigate funding source to alter toilet layout Adjust pressure of door to allow easier opening Staff handbook updated as a staff responsibility Cleaner Job Description altered to include awareness and action on this issue Look for alternative Premises Negotiate with Owner Ensure each service or programme conducted by ENET has access to training rooms at ground level Install ramp via applicable tender opportunity PD for staff to assist in evacuation process Consult with ACE Disability Network. Install visual alarms | June 2008 June 07 March 07 June 2007 February 2007 February 2007 March 2007 June 2009 June 2007 January 2007 May 2008 September 07 July 2007 | Electronic sliding door installed Work completed and positive feedback received from a person with a physical disability All rooms have a template Funding Submission lodged with positive outcome Pressure required to open door reduced by at least 25% No obstructions in corridors/Isles Job Description updated and signed off by Cleaner New premises obtained that do not have stairs and are friendly to PWD Lift installed by Owner and fully operational All programmes have access to a down stairs training room Ramp Installed Staff can assist PWD to exit using Emergency Fire Exit Visual Alarms installed | Allocation of money set aside over the next two financial years to pay for works undertaken. Consultation with Disability Resource Centre (DRC) Additional space created through the revamping of the reception area and/or an additional desk added to the reception area. IT software program and staff member with awareness of appropriate facility layout to accommodate students who are reliant on wheelchairs $1000.00 and staff member capable of writing tender Consultation with DRC Nil Nil $100.000.00 Consultation with DRC Time Timetables reworked to include this consideration $3,000.00 to write tender $500.00 for training $1500.00 | Finance Officer-Budget OH&S Officer to oversight Installation CEO to create the environment for change and Receptionist to coordinate completion OH&S Officer CEO Education Coordinator OH&S Officer Employment and Training Manager CEO Finance Officer (budget) CEO AQTF working group Emp & Train’g officer and CEO OH&S Officer OH&S Officer |

Communication

Aims:  To provide an employment, education and training environment that fosters strong participant communication that enhances each participant’s ability to maximise the learner’s goals.

Outcome 2 In a timely manner, Participants are provided with tools and equipment that directly assists them to communicate more effectively in groups and to more readily complete education and training tasks through the use of appropriate equipment.

| Communication Barriers | Improvement Strategies | Timeframe | Performance Indicators | Resources Needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Disability Resource Officer Sign Language Information Technology Hearing Loops Video Film Captions Telephone Typewriter | Appoint a staff member as a Disability Resource Officer. Staff member to research available resources for PWD including facilities that rent or loan equipment Consult with ACE Disability Network Purchase Auslan Book. Consult with ACE Disability Network Consult with Wesley Disability Services Purchase relevant IT equipment to assist participants in their day to day communication needs. Consult with Funding Bodies.(ACFE) Consult with ACE Disability Network and Wesley Disability Services Hire or purchase a hearing loop for use in training facility Consult with Funding Bodies.(ACFE) Consult with ACE Disability Network and Wesley Disability Services. Purchase digital top box for all TV’s – Videos Consult with Funding Bodies.(ACFE) Consult with ACE Disability Network and WDS Provide access to a telephone typewriter either through purchase or hire (Telstra) Consult with ACE Disability Network and WDS | November 2007 February 07 October 07 February 08 April 08 May 09 | Staff representative appointed and resource book/information available for use Auslan book/CD purchased At least one training computer in each lab has software installed to assist those with either a Audio or Visual disability Hearing loop purchased and operational or an account with a company has been set up for fast equipment hire. All audio visual equipment has provision for film captions Access to a TTW available | Nil $70.00 $500.00 $700.00 $600.00 $900.00 to $1,800 | CEO Education Coordinator Education Coordinator IT technician Education Coordinator Disability Resource Officer Education Coordinator Disability Resource Officer Employment and Training Manager |

Attitudinal

Aims:	That the ENET training facility provides for a positive training and placement environment where staff are continually reminded of the negative impact that attitudinal barriers have on the learner.

Outcome 3 All staff are made aware of the importance that ENET places on positive attitudes toward PWD, through Staff appointments, ENET’s Policy and Procedures relating to attitudinal barriers and professional development

| Attitudinal Barriers | Improvement Strategies | Timeframe | Performance Indicators | Resources Needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Staff Skill Base | Professional Development Include in Staff Job Interview process Heighten staff awareness of attitudinal barriers by writing a Policy and Procedures specific to awareness of attitudinal barriers | November 08 August 07 August 07 | At least one staff member from each department has undertaken PD Staff selection criteria updated to include Access and Equity Policy and Procedures written | $1000.00 Time Time | CEO AQTF Working Group AQTF Working Group |

Confidentiality

Aims:  That all staff are aware of their responsibility to maintain participant’s confidentiality.

That private participant information will only be made available to the necessary authorities, as per the Privacy Act 1988 and Privacy Amendment Federal Act 2000

Outcome 4   Prospective participant’s are able to enrol in a course or program at ENET, assured that their confidentiality will be maintained.

| Confidentiality Barriers | Improvement Strategies | Timeframe | Performance Indicators | Resources Needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Privacy Principles -staff awareness Privacy - hard copy storage -daily procedure -electronic storage - interview room -Open Plan office | Privacy Principles are made available to staff through the internet Signed Confidentiality statements placed at work station Hard copy personal information stored in secured filing cabinets at all times when not required. Participant information is not inadvertently left on desks All electronic Files/databases containing Participant names, addresses and telephone numbers be made more secure Rooms identified as appropriate for circumstances where there is a need to discuss someone’s personal details Restructure open plan office to improve privacy. Provide discreet screening or partitioning to section program areas | April 2007 May 2007 March 2007 April 2007 February 2007 February 2007 November 2007 | Privacy Principles placed on ENET’s website Each staff member has their signed confidentiality statements placed at their work station Each Program Coordinator has appropriate lockup storage units/filing cabinets. Lockable key storage devise purchased to house filing cabinet keys Staff Job description altered to provide for the checking of filing cabinet security prior to end of day business All Databases containing Participant information have password protection. Procedure in place that identifies staff who have access to files and passwords. Room selected for private interviews where necessary. Staff awareness of room availability. Allocated private space for each program organised Screening purchased and erected | Time Nil Audit of current storage system Purchase of keys where necessary $100.00 Nil Time Nil $ 5000.00 | CEO and IT tech support AQTF working group Program Coordinators CEO AQTF working group CEO Employment and Training Manager |

CONTACTS:

| Organisation | Address | Phone | Email | Website | Contact |
| --- | --- | --- | --- | --- | --- |
| WESLEY DISABILITY SERVICES | 154 Nicholson St Footscray 3011 | 9687 0033 | jobs@wesleyemployment.com.au | www.wesley.org.au | Gerrard McAdam |
| ACE DISABILITY NETWORK | 244 Flinders St Melbourne 3000 | 9916 5812 | info@acedisability.org.au | www.acedisability.org.au |  |
| CROSSLINK EMPLOYMENT SERVICES | 33A Taylor St Moonee Ponds 3039 | 9372 0675 | crosslink@aus.salvationarmy.org |  | Margaret Triplett |