MILPARA COMMUNITY HOUSE

21 Shellcott’s Road Korumburra Victoria 3950

Phone (03) 5655 2524

Fax 56581375

email: milpara@sympac.com.au

DISABILITY ACTION PLAN

approved by Committee at 10.08.06 Planning meeting

BACKGROUND

Milpara Community House came into being early in 1979 initially providing childcare and a playgroup.  The Neighbourhood House Co-ordination Program funded by the Department of Human Services provided funding to employ part-time staff to co-ordinate the community support activities at Milpara.  We are now funded by the Department for Victorian Communities.

In 1984 Milpara became a provider of adult and community education.  Adult education classes are both formal and informal and include computers, first aid, personal development, craft, cookery, budgeting, English as a second language and food handling courses etc.  Adult Education classes are subsidised through ACFE and are supplemented by other grants for specific projects eg: parenting courses.

Milpara Community House is registered as a Class 2 childcare centre and provides childcare for adult education classes and special events.  Milpara has a Playgroup which meets at Milpara on Tuesday mornings during school terms.

Milpara provides health information days for both English and Italian speaking people as well as Well Women's clinics.

In 2001 Milpara was officially appointed as Centrelink agency in recognition of the service provided to Centrelink clients over the past ten years.  The Centrelink agency provides access to Centrelink via telephone, fax and the Internet.  Forms can be lodged at Milpara as well as help with their completion and information obtained from trained agency staff.

A Family Counsellor from Kilmany Uniting Care is situated at Milpara and the Co-ordinators provide reception for the Family Counsellor and referral to other community support services.  We are also a venue for Financial counselling and other support services as required

Milpara provides a venue, has encouraged and often facilitated the following support groups:

- Korumburra Playgroup

- Personal Development Groups

- Sole Parent Support Service

Milpara Community House provides a range of community support activities such as the food bank, help with job application and resumes, advice and referral

- Vision “ All people living in the Korumburra  and District Community will have the opportunity to meet their full potential”

- Mission “To continually meet the changing social and educational needs of our Community”

AIMS

To create and maintain an environment for all House users which is committed to eliminating discrimination of any kind

CONSULTATION PROCESS

A special planning day and  workshop  was held on 7th May 2006 to look at  all the barriers and how to best overcome them. This workshop was conducted in consultation with the participation of people with disabilities from within the community and  house volunteers.  Our  house volunteers with disabilities offer regular advice on how processes can be improved.  Day to day practices are managed with this in mind.  We consult  frequently with staff, tutors, house users and volunteers to identify any discriminatory practices. We are also in liaison with Local Government and Health care workers.

POLICIES AND PROCEDURES

All policies, procedures and programs will take into account people with disabilities; and be required reading by staff, tutors, committee of management and volunteers.

Relevant Policies are: Access and Equity, Health and Safety, Student information and enrolment, Staff recruitment, Volunteer, Confidentiality, Grievance.

A sub -committee of the Committee of Management has been formed and is responsible for Policies and Procedures writing and reviewing.  Interested community members are also consulted.

ACTION PLAN

This plan addresses the issues involved with Enrolment, Participation, Curriculum Development Accreditation and Delivery; Elimination of Harassment and Discrimination and Student Support Services.

Enrolment

| Barriers | Strategies to overcome or remove the barriers | Timeframe | Performance Indicators | Resources needed | Responsible Person |
| --- | --- | --- | --- | --- | --- |
| Physical Access to Milpara CH | 1. Because the front door has two handles due to childcare requirements, we will install a door bell which will alert office staff 2. Tactile entry path outside and uneven surfaces in the house | October 2006 - DVC Grant for Disability Access. Implement 2007 | Tested and evaluated by at least two people (a) occupational therapist advice. (b) test by dight impaired person | Door Bell and review of door opening process. | Coordinators Co-ordinators |
| Physical Barrier Manual dexterity | Staff assistance with form completion | Immediate and ongoing | Personal feedback |  | Coordinator |
| Communication Barrier Advertising Material difficult to read | Produce in multiple media including CD Make interpreters available | Radio and print information available CD produced by October 2007 Advertise for interpreters in Term programme | Comprehension and awareness of programmes improved Feedback from users by survey | Technical advisor | To be arranged Coordinators |
| Attitudinal Barrier Staff lack of understanding of additional needs; students not accepting others' differences | Personal development for staff, tutors committee and house users. Polices and procedures clearly outlined and communicated | June 2007 | Improved understanding and communication | Workshop facilitator and posters and fliers | Committee, coordinators and house users |
| Confidentiality Barrier Careless talk and gossip | All staff and volunteers to read and sign off on confidentiality policy. Introduce a "Need to Know"" procedure. i.e. seek permission to advise other people of personal information | Immediate | Minimising gossip and careless talk | review induction procedures and refresher training | Coordinators |

Participation

| Barriers | Strategies to overcome or remove the barriers | Timeframe | Performance Indicators | Resources needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Communication Noise during classes and meetings | Tutor or chairperson to ensure that only one person talks at a time for hearing impaired people to participate | Immediate | Hearing impaired people to provide feedback | Special Needs indication on form prior to class and all participants made aware at start of class or meeting | Coordinator |
| Physical access Lighting | Ensure all rooms are well lit and relocate equipment if required and check outside venues before use | Immediate |  | Liaise with other service providers about suitable aids Do a physical audit with relevant participants | Coordinators |
| Communication Forms too difficult to read Learning disabilities | Enlarge print or use multiple media Tutor to be flexible in teaching methods | Reprint forms or course notes as necessary and Multiple media in 2007 |  | Special needs identified on enrolment form | Coordinators |
| Attitudinal. Impatience and inflexible teaching methods | Education to increase awareness and understanding. Tutor training and selection | June 2007 May 2008 | Advocates to assist with issues | Recruit professional people to counsel tutors and house users | Coordinators |

Curriculum Development, Accreditation and Delivery

| Barriers | Strategies to overcome or remove the barriers | Timeframe | Performance Indicators | Resources needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Physical Barrier -Inadequate public transport for staff and tutors without their own vehicles | Car pooling to convenient venues or organise PD to come to us. | Ongoing |  | training calendar | Coordinator |
| Communication Barrier. Under utilising Students as a resource Use of suitable curriculum | Recognising and valuing students knowledge and experience Add to scope of registration where possible | Ongoing Ongoing |  | Interactive learning programmes. (Apply for grant) Investigate resources to support curriculum | Coordinator |
| No Attitudinal and Confidentiality barriers |  |  |  |  |  |

Student Support Services

| Barriers | Strategies to overcome or remove the barriers | Timeframe | Performance Indicators | Resources needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| Physical Lack of awareness of resources available | Document all resources available and their locations | End 2008 |  | Recruit student to compile as part of a project | Coordinator |
| Physical Barrier. Inability to pay for classes | Negotiate Payment Plan and concessions | Immediate and ongoing | Increased participation | Nominate an advocate to negotiate for student if needed | Coordinator |
| Communication Barrier. Lack of consultation about services required | Convene an interactive workshop to discuss barriers and ways to overcome them | End of 2007 |  |  | Co-ordinator |
| Attitudinal Barrier. Parent with disabled child doesn't participate for fear of discrimination to the child | Parent awareness of our trained child care workers Parent to advise staff on communication methods and special needs for their child | Immediate and ongoing |  | Handout information to parents when they arrive or use our facilities and services | Coordinator |
| No confidentiality issues |  |  |  |  |  |

Harassment and Victimisation

| Barriers | Strategies to overcome or remove the barriers | Timeframe | Performance Indicators | Resources needed | Responsible Person/s |
| --- | --- | --- | --- | --- | --- |
| No physical barriers |  |  |  |  |  |
| Communication Barrier Perception is that there is no formal policy | Raise awareness of existing policy on unacceptable behaviour and make all house users aware of it. Educate staff and volunteers and students about their obligations not to harass or victimise others and their rights under our grievance policy. Sub Committee review policy where necessary. | Ongoing Ongoing |  |  | Policy sub-Committee Policy Sub-committee |

my documents/DisabilityAcPlan Policies